## Sheet1
Story # | As a <Type of user> | I want to <<some goal>> | so that <<reason>> | Date Introduced | Date Considered for Implementation | Developer Responsible for | Current Status
1 | user | have web based application | the web server environment is built | 1/30/2017 | 2/5/2017 | Cameron Ario | In progress
2 | user | load the webpage | the application can be run on the browser | 1/30/2017 | 2/5/2017 | Zhiyuan Li, XiangYang Guo | In progress
3 | user | see the block view enviroment | the block view environment is built up | 1/30/2017 | 2/5/2017 | Zhiyuan Li, XiangYang Guo | In progress
4 | user | see the graphical view enviroment | the graphical view environment is built up | 1/30/2017 |  |  | Not started
5 | user | execute the algorithm step by step | the algorithm is run step by step | 1/30/2017 |  |  | Not started
6 | user | execute the algorithm for a fixed number of times/steps | the algorithm is run in a fixed number of times/steps | 1/30/2017 |  |  | Not started
7 | user | see the movement through the block view | the agent is moved in the block view | 1/30/2017 |  |  | Not started
8 | user | see the movement through the graphical view | the agent is moved in the graphical view | 1/30/2017 |  |  | Not started
9 | user | see an old run | the information of the old run is stored | 1/30/2017 |  |  | Not started
10 | user | double-click on a node in the graph view | additional data on the agents in that node can be view | 1/30/2017 |  |  | Not started